## Start
ID | Description | Assigned To | Start Date | Planned End Date | Status | Budget | YTD Spend | Delta | Project Risk
1 | Project Alpha | Alice | 2024-05-01 | 2024-05-03 | Completed | 56000000 | 40000000 | 16000000 | 1
2 | Technical Integration | Bob | 2024-03-04 | 2024-05-05 | In Progress | 78000000 | 100000000 | -22000000 | 3
3 | Resource Allocation | Claire | 2024-05-05 | 2024-05-12 | Not Started | 1200000 | 1120000 | 80000 | 2
4 | Marketing Research | Alice | 2024-05-13 | 2024-05-13 | In Progress | 3000000 | 2000000 | 1000000 | 2
5 | Engineering Retrofit | Bob | 2024-05-14 | 2024-06-01 | Completed | 40000000 | 50000000 | -10000000 | 2
6 | Restructuring | Claire | 2024-02-02 | 2024-06-02 | Scheduled | 35000000 | 25000000 | 10000000 | 2
7 | Deal Review | Bob | 2024-03-14 | 2024-04-05 | In Progress | 2300000 | 1000000 | 1300000 | 2
Formulas:
Project Risk = (TODAY() > PMData3[[#This Row],[Planned End Date]]) + (PMData3[[#This Row],[Status]] <> "Completed") + (PMData3[[#This Row],[Delta]] < 0)

## Complete
ID | Description | Assigned To | Start Date | Planned End Date | Status | Budget | YTD Spend | Delta | Project Risk
1 | Project Alpha | Alice | 2024-05-01 | 2024-05-03 | Completed | 56000000 | 40000000 | 16000000 | 1
2 | Technical Integration | Bob | 2024-03-04 | 2024-05-05 | In Progress | 78000000 | 100000000 | -22000000 | 3
3 | Resource Allocation | Claire | 2024-05-05 | 2024-05-12 | Completed | 1200000 | 1120000 | 80000 | 1
4 | Marketing Research | Alice | 2024-05-13 | 2024-05-13 | In Progress | 3000000 | 2000000 | 1000000 | 2
5 | Engeineering Retrofit | Bob | 2024-05-14 | 2024-06-01 | Completed | 40000000 | 50000000 | -10000000 | 2
6 | Restructuring | Claire | 2024-02-02 | 2024-06-02 | Scheduled | 35000000 | 25000000 | 10000000 | 2
7 | Deal Review | Bob | 2024-03-14 | 2024-04-05 | In Progress | 2300000 | 1000000 | 1300000 | 2
Formulas:
Project Risk = (TODAY() >PMData[[#This Row],[Planned End Date]]) + (PMData[[#This Row],[Status]] <> "Completed") + ( PMData[[#This Row],[Delta]] < 0)