## Start
Project ID | Project Name | Progress | Budget | Expenses | Status | Start Date | End Date | Elapsed Days | EV | PV | CPI | SPI | Safety Incidents | Quality Score | Stakeholder Satisfaction
1 | Operation Quack Build | 0.51 | 573254 | 288669 | On Track | 2021-12-09 11:00 | 2025-09-01 11:00 | 880 | 292359.54 | 370384.3759 |  |  | 0 | 7 | 9
2 | Brickzilla | 0.92 | 449457 | 429002 | Delayed | 2022-02-23 11:00 | 2025-01-02 11:00 | 804 | 413500.44 | 346133.5517 |  |  | 1 | 8 | 10
3 | Mortar Kombat | 0.14 | 765987 | 101104 | On Track | 2023-04-01 11:00 | 2024-11-22 11:00 | 402 | 107238.18 | 512357.3611 |  |  | 0 | 7 | 7
4 | Concrete Jungle Boogie | 0.71 | 370936 | 254411 | On Track | 2023-10-04 11:00 | 2024-12-27 11:00 | 216 | 263364.56 | 178049.28 |  |  | 0 | 7 | 9
5 | The Mighty Duck Build | 0.6 | 339931 | 252688 | On Track | 2024-04-13 11:00 | 2025-06-05 11:00 | 24 | 203958.6 | 19517.5694 |  |  | 0 | 7 | 7
6 | Hard Hat Hilarity | 0.2 | 339629 | 104123 | On Track | 2021-12-22 11:00 | 2025-05-28 11:00 | 867 | 67925.8 | 235002.668 |  |  | 2 | 6 | 8
7 | Blockbuster Building | 0.82 | 305041 | 173911 | Completed | 2022-10-22 11:00 | 2025-02-23 11:00 | 563 | 250133.62 | 200863.255 |  |  | 0 | 6 | 6
8 | Trowel and Error | 0.86 | 798361 | 804774 | On Track | 2021-11-18 11:00 | 2026-12-30 11:00 | 901 | 686590.46 | 385076.6922 |  |  | 0 | 6 | 8
9 | The Unlevelers | 0.74 | 831912 | 795202 | On Track | 2023-01-23 11:00 | 2026-02-08 11:00 | 470 | 615614.88 | 351617.482 |  |  | 0 | 8 | 9
10 | Pylon Pals | 0.74 | 517113 | 446360 | On Track | 2022-06-07 11:00 | 2026-02-03 11:00 | 700 | 382663.62 | 270739.7906 |  |  | 1 | 10 | 7
11 | Mix-Up Mayhem | 0.87 | 168148 | 142685 | Completed | 2022-10-01 11:00 | 2027-01-14 11:00 | 584 | 146288.76 | 62706.5338 |  |  | 0 | 7 | 7
12 | Tower of Babble | 0.99 | 877089 | 807870 | On Track | 2021-12-16 11:00 | 2026-05-31 11:00 | 873 | 868318.11 | 470619.9736 |  |  | 0 | 7 | 10
13 | Foundation Follies | 0.23 | 748531 | 226643 | On Track | 2022-04-16 11:00 | 2025-01-30 11:00 | 752 | 172162.13 | 551858.149 |  |  | 0 | 8 | 7
14 | Wreck-it Raise | 0.02 | 351995 | 0 | Completed | 2023-08-31 11:00 | 2025-05-10 11:00 | 250 | 7039.9 | 142392.7994 |  |  | 0 | 7 | 10
15 | The Blueprint Buffoons | 0.21 | 778843 | 191296 | Completed | 2022-10-12 11:00 | 2026-04-26 11:00 | 573 | 163557.03 | 345415.6649 |  |  | 0 | 6 | 6
16 | Crane Craniums | 0.52 | 672843 | 348406 | Completed | 2024-01-23 11:00 | 2025-08-15 11:00 | 105 | 349878.36 | 123944.7632 |  |  | 0 | 10 | 9
17 | Nail It! | 0.01 | 356508 | 46990 | On Track | 2021-11-10 11:00 | 2025-07-01 11:00 | 909 | 3565.08 | 243841.8149 |  |  | 0 | 9 | 10
18 | Duct Tape Dynasty | 0.87 | 903591 | 750933 | Completed | 2022-04-25 11:00 | 2026-02-24 11:00 | 743 | 786124.17 | 479206.3619 |  |  | 0 | 7 | 6
19 | Plumb Busters | 0.29 | 996942 | 244968 | Completed | 2022-12-30 11:00 | 2025-03-30 11:00 | 494 | 289113.18 | 599865.2229 |  |  | 0 | 6 | 7
20 | Screw Loose Construction | 0.37 | 206530 | 84228 | On Track | 2023-03-18 11:00 | 2026-03-24 11:00 | 416 | 76416.1 | 77964.1379 |  |  | 0 | 9 | 7
21 | The Great Groutdoors | 0.01 | 704365 | 143257 | Completed | 2023-09-10 11:00 | 2024-12-27 11:00 | 240 | 7043.65 | 356640.5063 |  |  | 0 | 10 | 6
22 | Hammer Time Hustle | 0.63 | 922352 | 588550 | On Track | 2022-04-10 11:00 | 2026-08-13 11:00 | 758 | 581081.76 | 440821.4477 |  |  | 0 | 9 | 7
23 | Bulldoze and Banter | 0.59 | 560337 | 307263 | Delayed | 2022-07-13 11:00 | 2025-01-05 11:00 | 664 | 330598.83 | 410213.6362 |  |  | 1 | 6 | 6
24 | Beam Me Up | 0.2 | 824839 | 235698 | Completed | 2023-11-09 11:00 | 2026-03-31 11:00 | 180 | 164967.8 | 170069.8969 |  |  | 1 | 9 | 10
25 | Rebar Rebels | 0.32 | 905889 | 354939 | Delayed | 2022-11-04 11:00 | 2026-03-11 11:00 | 550 | 289884.48 | 407390.8013 |  |  | 0 | 8 | 10
26 | Wallflower Warriors | 0.75 | 559773 | 366569 | On Track | 2024-03-23 11:00 | 2027-01-16 11:00 | 45 | 419829.75 | 24479.8688 |  |  | 0 | 9 | 6
27 | Girder Giggles | 0.57 | 308261 | 159181 | Completed | 2022-11-20 11:00 | 2026-08-21 11:00 | 534 | 175708.77 | 120154.2876 |  |  | 0 | 7 | 10
28 | Masonry Mischief | 0.21 | 864469 | 276330 | On Track | 2023-11-20 11:00 | 2025-05-25 11:00 | 169 | 181538.49 | 264665.3279 |  |  | 0 | 7 | 10
29 | The Concrete Conundrum | 0.88 | 441097 | 407045 | Delayed | 2022-01-10 11:00 | 2026-03-19 11:00 | 848 | 388165.36 | 244637.1851 |  |  | 0 | 8 | 10
30 | Jackhammer Jamboree | 0.48 | 415139 | 96740 | On Track | 2022-05-30 11:00 | 2026-01-14 11:00 | 708 | 199266.72 | 221825.2166 |  |  | 0 | 6 | 8
31 | Paving Pandemonium | 0.9 | 271829 | 257748 | Completed | 2023-08-29 11:00 | 2025-08-31 11:00 | 252 | 244646.1 | 93452.8076 |  |  | 0 | 7 | 9
32 | Brick Brainiacs | 0.58 | 371836 | 250114 | Completed | 2024-02-02 11:00 | 2025-01-04 11:00 | 95 | 215664.88 | 104820.2374 |  |  | 0 | 10 | 7
33 | Ladder Laffs | 0.41 | 538974 | 175836 | Delayed | 2022-02-22 11:00 | 2026-04-08 11:00 | 805 | 220979.34 | 288096.992 |  |  | 0 | 7 | 8
34 | Plaster Blaster | 0.91 | 302283 | 295548 | On Track | 2022-09-28 11:00 | 2024-09-06 11:00 | 587 | 275077.53 | 250268.1537 |  |  | 1 | 7 | 10
35 | Flue Crew Follies | 0.59 | 296769 | 230658 | Completed | 2022-06-16 11:00 | 2026-08-24 11:00 | 691 | 175093.71 | 134030.9667 |  |  | 0 | 6 | 6
36 | The Build Bafflers | 0.79 | 661353 | 548683 | Delayed | 2022-10-19 11:00 | 2025-09-25 11:00 | 566 | 522468.87 | 349184.5131 |  |  | 0 | 9 | 10
37 | The Framing Funnies | 0.14 | 323165 | 25025 | Completed | 2022-10-02 11:00 | 2025-08-01 11:00 | 583 | 45243.1 | 182210.0532 |  |  | 0 | 7 | 9
38 | Drywall Daydreams | 0.61 | 723587 | 403583 | Completed | 2021-09-18 11:00 | 2025-12-01 11:00 | 962 | 441388.07 | 453479.2795 |  |  | 1 | 8 | 10
39 | Level Up | 0.61 | 635822 | 388680 | On Track | 2022-07-22 11:00 | 2025-02-08 11:00 | 655 | 387851.42 | 446849.1524 |  |  | 0 | 9 | 6
40 | Concrete Conviviality | 0.46 | 587879 | 292633 | Completed | 2022-02-22 11:00 | 2025-10-08 11:00 | 805 | 270424.34 | 357433.9841 |  |  | 0 | 10 | 9
41 | The Scaffold Scallywags | 0.61 | 664685 | 409634 | On Track | 2024-03-31 11:00 | 2026-08-01 11:00 | 37 | 405457.85 | 28831.5885 |  |  | 1 | 6 | 10
42 | Hardcore Hardware | 0.5 | 882038 | 485262 | Completed | 2022-08-17 11:00 | 2025-06-06 11:00 | 629 | 441019 | 541798.7324 |  |  | 0 | 10 | 9
43 | Tool Time Trials | 0.54 | 453531 | 238242 | Delayed | 2022-10-20 11:00 | 2025-06-07 11:00 | 565 | 244906.74 | 266644.1363 |  |  | 0 | 9 | 7
44 | High Beam Hijinks | 0.63 | 363160 | 235350 | Completed | 2023-05-24 11:00 | 2024-09-06 11:00 | 349 | 228790.8 | 269093.0785 |  |  | 0 | 9 | 7
45 | Floorboard Frolics | 0.02 | 679879 | 79193 | On Track | 2022-02-20 11:00 | 2026-01-19 11:00 | 807 | 13597.58 | 383948.4625 |  |  | 0 | 9 | 10
46 | Erector Set Escapades | 1 | 320884 | 286715 | Completed | 2021-09-13 11:00 | 2026-01-31 11:00 | 967 | 320884 | 193813.1343 |  |  | 0 | 10 | 9
47 | Shingle All The Way | 0.5 | 123247 | 62963 | Delayed | 2023-06-02 11:00 | 2026-12-24 11:00 | 340 | 61623.5 | 32209.0546 |  |  | 0 | 9 | 6
48 | Caulk Con Artists | 0.06 | 124300 | 8773 | Completed | 2022-07-28 11:00 | 2024-08-05 11:00 | 649 | 7458 | 109161.9756 |  |  | 0 | 10 | 10
49 | Groundbreakers Guffaws | 0.2 | 567281 | 165684 | Completed | 2022-12-09 11:00 | 2026-04-15 11:00 | 515 | 113456.2 | 238879.5707 |  |  | 1 | 9 | 7
50 | Pilot Project Puns | 0.72 | 707086 | 493071 | Delayed | 2023-05-16 11:00 | 2024-09-06 11:00 | 357 | 509101.92 | 526993.1148 |  |  | 0 | 8 | 7

## Complete
Project ID | Project Name | Progress | Budget | Expenses | Status | Start Date | End Date | Elapsed Days | Earned Value | Planned Value | CPI | SPI | Safety Incidents | Quality Score | Stakeholder Satisfaction
1 | Operation Quack Build | 51% | 573254 | 288669 | On Track | 2021-12-09 11:00 | 2025-09-01 11:00 | 880 | 292359.54 | 370384.3759 | 1.0128 | 0.78934 | 0 | 7 | 9
2 | Brickzilla | 92% | 449457 | 429002 | Delayed | 2022-02-23 11:00 | 2025-01-02 11:00 | 804 | 413500.44 | 346133.5517 | 0.96387 | 1.1946 | 1 | 8 | 10
3 | Mortar Kombat | 14% | 765987 | 101104 | On Track | 2023-04-01 11:00 | 2024-11-22 11:00 | 402 | 107238.18 | 512357.3611 | 1.0607 | 0.2093 | 0 | 7 | 7
4 | Concrete Jungle Boogie | 71% | 370936 | 254411 | On Track | 2023-10-04 11:00 | 2024-12-27 11:00 | 216 | 263364.56 | 178049.28 | 1.0352 | 1.4792 | 0 | 7 | 9
5 | The Mighty Duck Build | 60% | 339931 | 252688 | On Track | 2024-04-13 11:00 | 2025-06-05 11:00 | 24 | 203958.6 | 19517.5694 | 0.80716 | 10.45 | 0 | 7 | 7
6 | Hard Hat Hilarity | 20% | 339629 | 104123 | On Track | 2021-12-22 11:00 | 2025-05-28 11:00 | 867 | 67925.8 | 235002.668 | 0.65236 | 0.28904 | 2 | 6 | 8
7 | Blockbuster Building | 82% | 305041 | 173911 | Completed | 2022-10-22 11:00 | 2025-02-23 11:00 | 563 | 250133.62 | 200863.255 | 1.4383 | 1.2453 | 0 | 6 | 6
8 | Trowel and Error | 86% | 798361 | 804774 | On Track | 2021-11-18 11:00 | 2026-12-30 11:00 | 901 | 686590.46 | 385076.6922 | 0.85315 | 1.783 | 0 | 6 | 8
9 | The Unlevelers | 74% | 831912 | 795202 | On Track | 2023-01-23 11:00 | 2026-02-08 11:00 | 470 | 615614.88 | 351617.482 | 0.77416 | 1.7508 | 0 | 8 | 9
10 | Pylon Pals | 74% | 517113 | 446360 | On Track | 2022-06-07 11:00 | 2026-02-03 11:00 | 700 | 382663.62 | 270739.7906 | 0.8573 | 1.4134 | 1 | 10 | 7
11 | Mix-Up Mayhem | 87% | 168148 | 142685 | Completed | 2022-10-01 11:00 | 2027-01-14 11:00 | 584 | 146288.76 | 62706.5338 | 1.0253 | 2.3329 | 0 | 7 | 7
12 | Tower of Babble | 99% | 877089 | 807870 | On Track | 2021-12-16 11:00 | 2026-05-31 11:00 | 873 | 868318.11 | 470619.9736 | 1.0748 | 1.8451 | 0 | 7 | 10
13 | Foundation Follies | 23% | 748531 | 226643 | On Track | 2022-04-16 11:00 | 2025-01-30 11:00 | 752 | 172162.13 | 551858.149 | 0.75962 | 0.31197 | 0 | 8 | 7
14 | Wreck-it Raise | 2% | 351995 | 0 | Completed | 2023-08-31 11:00 | 2025-05-10 11:00 | 250 | 7039.9 | 142392.7994 | 0 | 0.04944 | 0 | 7 | 10
15 | The Blueprint Buffoons | 21% | 778843 | 191296 | Completed | 2022-10-12 11:00 | 2026-04-26 11:00 | 573 | 163557.03 | 345415.6649 | 0.85499 | 0.47351 | 0 | 6 | 6
16 | Crane Craniums | 52% | 672843 | 348406 | Completed | 2024-01-23 11:00 | 2025-08-15 11:00 | 105 | 349878.36 | 123944.7632 | 1.0042 | 2.8229 | 0 | 10 | 9
17 | Nail It! | 1% | 356508 | 46990 | On Track | 2021-11-10 11:00 | 2025-07-01 11:00 | 909 | 3565.08 | 243841.8149 | 0.075869 | 0.01462 | 0 | 9 | 10
18 | Duct Tape Dynasty | 87% | 903591 | 750933 | Completed | 2022-04-25 11:00 | 2026-02-24 11:00 | 743 | 786124.17 | 479206.3619 | 1.0469 | 1.6405 | 0 | 7 | 6
19 | Plumb Busters | 29% | 996942 | 244968 | Completed | 2022-12-30 11:00 | 2025-03-30 11:00 | 494 | 289113.18 | 599865.2229 | 1.1802 | 0.48196 | 0 | 6 | 7
20 | Screw Loose Construction | 37% | 206530 | 84228 | On Track | 2023-03-18 11:00 | 2026-03-24 11:00 | 416 | 76416.1 | 77964.1379 | 0.90725 | 0.98014 | 0 | 9 | 7
21 | The Great Groutdoors | 1% | 704365 | 143257 | Completed | 2023-09-10 11:00 | 2024-12-27 11:00 | 240 | 7043.65 | 356640.5063 | 0.049168 | 0.01975 | 0 | 10 | 6
22 | Hammer Time Hustle | 63% | 922352 | 588550 | On Track | 2022-04-10 11:00 | 2026-08-13 11:00 | 758 | 581081.76 | 440821.4477 | 0.98731 | 1.3182 | 0 | 9 | 7
23 | Bulldoze and Banter | 59% | 560337 | 307263 | Delayed | 2022-07-13 11:00 | 2025-01-05 11:00 | 664 | 330598.83 | 410213.6362 | 1.0759 | 0.80592 | 1 | 6 | 6
24 | Beam Me Up | 20% | 824839 | 235698 | Completed | 2023-11-09 11:00 | 2026-03-31 11:00 | 180 | 164967.8 | 170069.8969 | 0.69991 | 0.97 | 1 | 9 | 10
25 | Rebar Rebels | 32% | 905889 | 354939 | Delayed | 2022-11-04 11:00 | 2026-03-11 11:00 | 550 | 289884.48 | 407390.8013 | 0.81672 | 0.71156 | 0 | 8 | 10
26 | Wallflower Warriors | 75% | 559773 | 366569 | On Track | 2024-03-23 11:00 | 2027-01-16 11:00 | 45 | 419829.75 | 24479.8688 | 1.1453 | 17.15 | 0 | 9 | 6
27 | Girder Giggles | 57% | 308261 | 159181 | Completed | 2022-11-20 11:00 | 2026-08-21 11:00 | 534 | 175708.77 | 120154.2876 | 1.1038 | 1.4624 | 0 | 7 | 10
28 | Masonry Mischief | 21% | 864469 | 276330 | On Track | 2023-11-20 11:00 | 2025-05-25 11:00 | 169 | 181538.49 | 264665.3279 | 0.65696 | 0.68592 | 0 | 7 | 10
29 | The Concrete Conundrum | 88% | 441097 | 407045 | Delayed | 2022-01-10 11:00 | 2026-03-19 11:00 | 848 | 388165.36 | 244637.1851 | 0.95362 | 1.5867 | 0 | 8 | 10
30 | Jackhammer Jamboree | 48% | 415139 | 96740 | On Track | 2022-05-30 11:00 | 2026-01-14 11:00 | 708 | 199266.72 | 221825.2166 | 2.0598 | 0.89831 | 0 | 6 | 8
31 | Paving Pandemonium | 90% | 271829 | 257748 | Completed | 2023-08-29 11:00 | 2025-08-31 11:00 | 252 | 244646.1 | 93452.8076 | 0.94917 | 2.6179 | 0 | 7 | 9
32 | Brick Brainiacs | 58% | 371836 | 250114 | Completed | 2024-02-02 11:00 | 2025-01-04 11:00 | 95 | 215664.88 | 104820.2374 | 0.86227 | 2.0575 | 0 | 10 | 7
33 | Ladder Laffs | 41% | 538974 | 175836 | Delayed | 2022-02-22 11:00 | 2026-04-08 11:00 | 805 | 220979.34 | 288096.992 | 1.2567 | 0.76703 | 0 | 7 | 8
34 | Plaster Blaster | 91% | 302283 | 295548 | On Track | 2022-09-28 11:00 | 2024-09-06 11:00 | 587 | 275077.53 | 250268.1537 | 0.93074 | 1.0991 | 1 | 7 | 10
35 | Flue Crew Follies | 59% | 296769 | 230658 | Completed | 2022-06-16 11:00 | 2026-08-24 11:00 | 691 | 175093.71 | 134030.9667 | 0.75911 | 1.3064 | 0 | 6 | 6
36 | The Build Bafflers | 79% | 661353 | 548683 | Delayed | 2022-10-19 11:00 | 2025-09-25 11:00 | 566 | 522468.87 | 349184.5131 | 0.95222 | 1.4963 | 0 | 9 | 10
37 | The Framing Funnies | 14% | 323165 | 25025 | Completed | 2022-10-02 11:00 | 2025-08-01 11:00 | 583 | 45243.1 | 182210.0532 | 1.8079 | 0.2483 | 0 | 7 | 9
38 | Drywall Daydreams | 61% | 723587 | 403583 | Completed | 2021-09-18 11:00 | 2025-12-01 11:00 | 962 | 441388.07 | 453479.2795 | 1.0937 | 0.97334 | 1 | 8 | 10
39 | Level Up | 61% | 635822 | 388680 | On Track | 2022-07-22 11:00 | 2025-02-08 11:00 | 655 | 387851.42 | 446849.1524 | 0.99787 | 0.86797 | 0 | 9 | 6
40 | Concrete Conviviality | 46% | 587879 | 292633 | Completed | 2022-02-22 11:00 | 2025-10-08 11:00 | 805 | 270424.34 | 357433.9841 | 0.92411 | 0.75657 | 0 | 10 | 9
41 | The Scaffold Scallywags | 61% | 664685 | 409634 | On Track | 2024-03-31 11:00 | 2026-08-01 11:00 | 37 | 405457.85 | 28831.5885 | 0.98981 | 14.063 | 1 | 6 | 10
42 | Hardcore Hardware | 50% | 882038 | 485262 | Completed | 2022-08-17 11:00 | 2025-06-06 11:00 | 629 | 441019 | 541798.7324 | 0.90883 | 0.81399 | 0 | 10 | 9
43 | Tool Time Trials | 54% | 453531 | 238242 | Delayed | 2022-10-20 11:00 | 2025-06-07 11:00 | 565 | 244906.74 | 266644.1363 | 1.028 | 0.91848 | 0 | 9 | 7
44 | High Beam Hijinks | 63% | 363160 | 235350 | Completed | 2023-05-24 11:00 | 2024-09-06 11:00 | 349 | 228790.8 | 269093.0785 | 0.97213 | 0.85023 | 0 | 9 | 7
45 | Floorboard Frolics | 2% | 679879 | 79193 | On Track | 2022-02-20 11:00 | 2026-01-19 11:00 | 807 | 13597.58 | 383948.4625 | 0.1717 | 0.035415 | 0 | 9 | 10
46 | Erector Set Escapades | 100% | 320884 | 286715 | Completed | 2021-09-13 11:00 | 2026-01-31 11:00 | 967 | 320884 | 193813.1343 | 1.1192 | 1.6556 | 0 | 10 | 9
47 | Shingle All The Way | 50% | 123247 | 62963 | Delayed | 2023-06-02 11:00 | 2026-12-24 11:00 | 340 | 61623.5 | 32209.0546 | 0.97873 | 1.9132 | 0 | 9 | 6
48 | Caulk Con Artists | 6% | 124300 | 8773 | Completed | 2022-07-28 11:00 | 2024-08-05 11:00 | 649 | 7458 | 109161.9756 | 0.85011 | 0.06832 | 0 | 10 | 10
49 | Groundbreakers Guffaws | 20% | 567281 | 165684 | Completed | 2022-12-09 11:00 | 2026-04-15 11:00 | 515 | 113456.2 | 238879.5707 | 0.68477 | 0.47495 | 1 | 9 | 7
50 | Pilot Project Puns | 72% | 707086 | 493071 | Delayed | 2023-05-16 11:00 | 2024-09-06 11:00 | 357 | 509101.92 | 526993.1148 | 1.0325 | 0.96605 | 0 | 8 | 7
Total | [10 empty] | 0.92067 | 1.1106 | 3 | 8.1429 | 8.0476

## KPI Dashboard
Cost Performance Index | Schedule Performance Index | Safety Incident Counts
0.92067 | 1.1106 | 3
Quality Score | Stakeholder Satisfaction
8.1429 | 8.0476
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.